## 2020 reviewfin
Development Dimension 1:Economic Development
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 1.1: Ensure improved fiscal performance and sustainability
1.1.1 | Review Revenue Improvement Plan for 2019 and prepare 2021 Revenue Improvement plan | Main Administration | Revenue Improvement Plan for 2019 reviewed and 2021 prepared |  |  |  |  | 2000 | I.G.F | Budget Dept | Finance Dept, Revenue Collectors | fin | imp
1.1.2 | Update revenue database and renew software lincense for Property Rate collection | Main Administration | Revenue Database Updated |  |  |  |  | 18000 | IGF | Finance Dept | Revenue Collectors | fin | imp
1.1.3 | Prepare and Gazette 2020 Fee Fixing Resolution and Composite Budget | Main Administration | 2020 Fee Fixing and Composite Budget Prepared |  |  |  |  | 22000 | I.G.F | Budget Dept | Assembly members, Traders | fin | imp
1.1.4 | Prepare 2020 supplementary estimates for DACF and revise 2020 Budget | Main Administration | 2020 Supplementary estimates prepared and budget revised |  |  |  |  | 12000 | I.G.F | Budget Dept | Finance Dept, Assembly members | fin | imp
1.1.5 | Review monthly trial balance and pre audit payment vouchers | Main Administration | Monthly trial balance reviewed and payment vouchers pre audited |  |  |  |  | 24000 | I.G.F | Finance Dept | Internal Audit, Budget Dept |  | imp
1.1.6 | Facilitate the holding of quarterly Budget Committee meetings | Main Administration | Quarterly Budget Committee meetings held |  |  |  |  | 5000 | I.G.F | Budget Dept | Internal Audit, Finance Dept | fin | imp
1.1.7 | Post-audit procurements, Kejetia (Race Course) terminal and all the sub metros | Kejetia (Race Course) & 5 sub metros | Procurements, Kejetia (Race Couse) and Submetros post audited |  |  |  |  | 4500 | I.G.F | Internal Audit | Auditor Generals Dept Finance,Budget | fin | imp
1.1.8 | Conduct Monitoring & Evaluation of Assembly activities | All Sub Metros | M&E Conducted for Assembly activies |  |  |  |  | 40000 | DACF | Planning Unit | Audit, Budget Dept, Beneficiaries | fin | imp
1.1.9 | Prepare expenditure warrants for all Assembly expenditure | Main Administration | Expenditure Warrants prepared |  |  |  |  | 12000 | I.G.F | Budget Dept | Finance Dept, Internal Audit | fin | imp
1.1.10 | Conduct Revaluation of Properties in the Kumasi Metropolis | Metro Wide | Revaluation of Properties conducted |  |  |  |  | 500000 | I.G.F/ DACF | Finance/LVD | MPCU, Assembly | gov | imp
Objective 1.2: Enhance Business Enabling Environment
1.2.1 | Update data on SMEs | Main Administration | Database Updated |  |  |  |  | 5000 | I.G.F | Trade & Investment committee | ASSI, AGI | led | imp
1.2.2 | Organise a business forum to enhance public and private sector synergies | Main Administration | Business forum organized |  |  |  |  | 25000 | DACF | Trade & Investment committee | NBSSI, ASSI, AGI | led | imp
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 1.3: Diversify and expand the tourism industry for economic development
1.3.1 | Organize Training on Business Development Services | All Sub Metros | Training organized |  |  |  |  | 5000 | I.G.F | Trade & Investment committee | Ghana Tourism Board | led | imp
1.3.2 | Develop & Distribute Kumasi Tourism & Investment guide brochures | All Sub Metros | Brochures developed and distributed |  |  |  |  | 15000 | I.G.F | Trade & Investment committee | Ghana Tourism Board | led | imp
Objective 1.4:Improve production efficiency and yield
1.4.1 | Conduct farm and home visits to planting for food and jobs farmers to advice them on farming related issues and give solution to their problems | All Sub-Metros | Farm and Home visits conducted |  |  |  |  | 15600 | MAG | Agric Dept | Beneficiaries | AG | imp
1.4.2 | Conduct 12 pesticide residue analysis for four major vegetables | Abinkyi,Bantama, Asafo and Central Market | 12 Lab analysis on pesticide residues conducted |  |  |  |  | 18000 | DACF | Agric Dept | Beneficiaries Consultants | AG | imp
1.4.3 | Conduct 8 demonstrations and train 250 urban dwellers in 4 operational zones on urban and peri urban agric | Santasi, Buokrom, Amanfrom and Nhyiaeso | 8 demonstrations conducted and 250 urban dwellers trained |  |  |  |  | 12000 | IGF | Agric Dept | Beneficiaries | AG | imp
1.4.4 | Conduct 16 plant clinics and 5 yield studies | All Sub-Metros | 16 plant clinics and 5 yield studies conducted |  |  |  |  | 3600 | MAG | Agric Dept | MOFA | AG | imp
1.4.5 | Train 30 farmers on how to use the i-2 vaccine in controlling Newcastle disease and carry out vaccination | All Sub-Metros | 30 farmers trained on use of i-2 vaccine for controlling new castle disease |  |  |  |  | 1000 | MAG | Agric Dept | Beneficiaries | AG | imp
1.4.6 | Establish 14 maize & 14 vegetable demonstrations & conduct one planning session | All Sub-Metros | 28 demonstrations established and one planning session held |  |  |  |  | 7600 | MAG | Agric Dept | Beneficiaries | AG | imp
1.4.7 | Carryout Disease surveillance, vaccination of 1,000 ruminants against PPR, CBPP, Rabbies | All Sub-Metros | Survellance and vaccination carried out |  |  |  |  | 38600 | IGF/MAG | Agric Dept | Beneficiaries | AG | imp
1.4.8 | Train 100 women farmers and market women in promotion | All Sub-Metros | Training conducted |  |  |  |  | 2100 | MAG | Agric Dept | Beneficiaries | AG | imp
1.4.9 | Sensitize and train 65 poultry and pig farmers on various topics | All Sub-Metros | Trainning organized |  |  |  |  | 2100 | MAG | Agric Dept | Beneficiaries | AG | imp
1.4.10 | Establish DECAT Office | Metro Office | Office established |  |  |  |  | 7000 | MAG | Agric Dept | Beneficiaries | AG | imp | 7200000
1.4.11 | Organize 12 monthly technical review meetings | Metro Office | Monthly meetings |  |  |  |  | 8280 | MAG | Agric Dept | Beneficiaries |  | imp | 67380
1.4.12 | Organise celebration of National Farmers Day | Selected Community | National Farmers Day organized |  |  |  |  | 50000 | DACF | Agric Dept | Central Administration | AG | imp | 98500
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 1.5: Enhance Domestic Trade
1.5.1 | Complete the Reconstruction of 3No. Markets | Central Market Krofofrom Sokoban | Sheds and Stalls provided |  |  |  |  | 6000000 | PPP/GOG | Works Dept | Beneficiaries, | AG | imp
Development Dimension 2:Social Development
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 2.1: Enhance inclusive and equitable access to, and participation in quality education at all levels
2.1.1 | Complete the construction of 3No. 3-unit KG Blocks | Old Amakom Apraman/ Santasi M/A | Classroom block |  |  |  |  | 1500000 | DACF/ RFG | Education Dept | Works Dept/ Beneficiaries | ED | 1000000 | imp
2.1.2 | Complete the construction of 1No. 6-unit Classroom Blocks | Fankyenebra | Classroom block |  |  |  |  | 700000 | DACF | Education Dept | Works Dept/ Beneficiaries | ED | 8515000 | imp
2.1.3 | Rehabilitate 4No. Schools in the Kumasi Metropolis | Opoku Ware Basic Akosa M/A Adumanu Pataase | Classroom blocks |  |  |  |  | 1000000 | DACF | Education Dept | Works Dept/ Beneficiaries
2.1.4 | Construct 3No. School/Communal Parks (Grass & Astroturf) | Subin Nhyaeso Bantama | School/Community Parks |  |  |  |  | 300000 | IGF | Education Dept | Works Dept/ Beneficiaries |  | 2925000 | imp
2.1.5 | Procure 1,000 No. Dual/Mono Desk | All Sub-Metros | Furniture |  |  |  |  | 300000 | DACF | Education Dept | Works Dept/ Beneficiaries |  | 63000 | imp
2.1.6 | Conduct B.E.C.E. Mock Examinations for final year students in Junior High Schools | All Sub-Metros | Mock examinations conducted |  |  |  |  | 40, 536.00 | DACF | Education Dept | Assembly members | ED | 40000 | imp
2.1.7 | Support the organisation of "My First Day at School" in 5 basic schools to welcome KG and Primary 1 pupils | All Sub-Metros | "My First Day at School" supported |  |  |  |  | 9000 | I.G.F | Education Dept | Central Administration | ED | 300000 | imp
2.1.8 | Monitor the implementation of the School Feeding Programme in selected schools | All Sub-Metros | School Feeding carried out |  |  |  |  | 5000 | IGF/DACF | Education Dept | Administration | ED | 1800000 | imp
Objective 2.3: Ensure the reduction of new HIV and AIDS/STIs infections, especially among the vulnerable groups
2.3.1 | Conduct Quarterly MAC meetings and Organize two stakeholder performance review meetings | Main Administration | MAC and performance review meetings organized |  |  |  |  | 10000 | DACF | Health Dept | AIDS Desk Officer | HEA |  | imp
2.3.2 | Conduct / Hold Community Durbars and Radio Talk Shows on stigmatization and discrimination in all sub-metros | Main Administration | Communiyty Durbars held |  |  |  |  | 20000 | DACF | Health Dept | AIDS Desk Officer | HEA | 15000 | imp
2.3.3 | Organize quarterly screening and testing of HIV, TB in all Sub - Metros | All Sub-Metros | Quarterly screening and testing organized |  |  |  |  | 10000 | DACF | Health Dept | AIDS Desk Officer | HEA | 300000 | imp
2.3.4 | Organize Sensitization programmes in Schools on stigmatization and discrimination | All Sub-Metros | Quarterly screening and testing organized |  |  |  |  | 10000 | DACF | Health Dept | AIDS Desk Officer |  | 1800000
Objective 2.4: Reduce disability morbidity, and mortality
2.4.1 | Conduct education on cancer, DM and Hypertension in all town councils | Metro Wide | Education on cancer conducted |  |  |  |  | 5000 | I.G.F | Health Dept | G.H.S |  |  | imp
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 2.5: Promote economic empowerment of women.
2.5.1 | Organize Breast Cancer Awareness & Screening in 6 Markets in the Kumasi Metropolis | Main Administration | Awareness & Screening organized |  |  |  |  | 15000 | I.G.F | Gender Desk | G.H.S | GEN | 25000 | imp
2.5.2 | Organise a sensitization walk on family planning and child spacing | All Sub-Metros | 200 people participated |  |  |  |  | 10000 | I.G.F | Gender Desk Officer | Health Dept, | GEN | 55000 | imp
Objective 2.6:Attain gender equality and equity in political, social and economic development systems and outcomes
2.6.1 | Sensitize and empower 8 women groups on Local Governance | All Sub-Metros | 8 groups sensitised |  |  |  |  | 8000 | I.G.F | Gender Desk Officer | Social Welfare, Community Dev't |  | 8000 | imp
2.6.2 | Celebrate International Day of the Girl Child | All Sub-Metros | Day celebrated |  |  |  |  | 12000 | I.G.F | Gender Desk Officer | Social Welfare, Community Dev't |  |  | imp
2.6.3 | Organize women in Management training for all Assembly Women & Staff of the Assembly | Main Administration | Training organized |  |  |  |  | 10000 | I.G.F | Gender Desk Officer | Planning Unit |  |  | imp
2.6.4 | Prepare Gender profile for the Kumasi Metropolitan Assembly | Main Administration | Gender Profile |  |  |  |  | 2000 | I.G.F | Gender Desk Officer | Planning Unit |  |  | imp
Objective 2.7:Strengthen social protection, especially for children, women, persons with disability and the elderly
2.7.1 | Carry out LEAP activities to benefit 2000 beneficiaries | All Sub-Metros | LEAP activities carried out |  |  |  |  | 5000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
Objective 2.8: Eradicate poverty in all its forms and dimensions
2.8.1 | To render personal welfare services to 900 indigents and link them up to NHIS | All Sub-Metros | 900 indigents provided with personal welfare services |  |  |  |  | 5000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
2.8.2 | To provide hospital welfare services for 1700 patients without support and mental health patients | All Sub-Metros | Hospital welfare services provided |  |  |  |  | 10000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
Objective 2.9: Ensure effective child protection and family welfare system
2.9.1 | To monitor and support the growth and development of 250 orphans and street children | All Sub-Metros | 1300 orphans and street children supported |  |  |  |  | 3000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
Objective 2.10: Ensure the rights and entitlements of children
2.10.1 | Organise talks session on child abuse, labour and molestation in 100 schools. | All Sub-Metros | Talk sessions organized |  |  |  |  | 10000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
2.10.2 | Highlight the responsiblities of the child at home and in school within 20 selected schools | All Sub-Metros | 20 schools visited |  |  |  |  | 5000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
2.10.3 | Visit and educate 50 household on parental role on child management. | All Sub-Metros | 50 households educated |  |  |  |  | 4000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
2.10.4 | Monitor, register and renew certificate of 90 day care centres and organise training for 50 of them | All Sub-Metros | Registration, renewal of certificates and training done |  |  |  |  | 3000 | I.G.F | SW&CD | FBOs/NGOs/ CBOs | VUL |  | imp
Objective 2.11: Promote full participation of PWDs in social and economic development of the country
2.11.1 | Organise skill training programmes for 480 persons with disabilities (PWDs) and link them up to NHIS | All Sub-Metros | 480 PWDs trained |  |  |  |  | 7000 | DACF | Social Welfare Dept | Associations of PWDs | VUL |  | imp
2.11.2 | Identify the needs of 178 persons with disability and support them | All Sub-Metros | 178 PWDs supported |  |  |  |  | 79000 | DACF | Social Welfare Dept | Associations of PWDs | VUL |  | imp
Objective 2.12: Improve access to safe and reliable water supply services for all
2.12.1 | Construct 10 No. Mechanised Boreholes with overhead tanks across the metropolis | All Sub-Metros | Boreholes |  |  |  |  | 600000 | DACF | Works Dept | GWCL | WS |  | imp
Objective 2.13: Improve access to improved and reliable environmental sanitation services
2.13.1 | Visit 5 radio stations to discuss sanitation issues | All Sub-Metros | Radio recordings |  |  |  |  | 2500 | I.G.F | EHU | P.R.O | WS |  | imp
2.13.2 | Organise durbars for 11 town councils on environmental sanitation | All Sub-Metros | Durbars organised |  |  |  |  | 10000 | I.G.F | EHU | P.R.O, ISD | WS |  | imp
2.13.3 | Develop and distribute education materials on improved sanitation practices | All Sub-Metros | Publications |  |  |  |  | 3000 | I.G.F | EHU | P.R.O | WS |  | imp
2.13.4 | Routinely inspect all food premises at sub-metro level | All Sub-Metros | Inspection reports |  |  |  |  | 1500 | I.G.F | EHU | Legal Dept | WS |  | imp
2.13.5 | Organise quarterly public sensitization on food hygiene through radio, public announcement vans, information centers | All Sub-Metros | Sensitization orgainised |  |  |  |  | 2000 | I.G.F | EHU | P.R.O, Information Services Dept | WS |  | imp
2.13.6 | Collect, compile and collate data on all food establishements and potential noise emmitters | All Sub-Metros | Database |  |  |  |  | 50000 | I.G.F | EHU | GSS, Planning Unit | WS |  | imp
2.13.7 | Identify and select laboratories for the screening exercise and provide certificates to those screened | All Sub-Metros | Screening exercise done |  |  |  |  | 500 | I.G.F | EHU | GSS, Planning Unit | WS |  | imp
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
2.13.8 | Organise food handlers into group at the Town Councils to desseminate information of screening and registration | All Sub-Metros | Food handlers grouped |  |  |  |  | 2000 | I.G.F | EHU | P.R.O, Information Services Dept | WS |  | imp
2.13.9 | Organize quarterly meetings/training with sanitation service providers | Main Administration | Meetings organised |  |  |  |  | 15000 | I.G.F | Waste Mgt Dept | ESMA | WS |  | imp
2.13.10 | Support the evacuation of refuse and clean up activities in the metropolis | All Sub-Metros | Evacuation supported |  |  |  |  | 200000 | DACF | Waste Mgt Dept | ESPA, EHU | WS |  | imp
2.13.11 | Operation & Maintenance of Land fill site and Heavy Duty Equipment | Oti | Land Fill |  |  |  |  | 3000000 | DACF | Waste Mgt Dept | PWCC | WS |  | imp
2.13.12 | Conduct regular fumigation exercise | All Sub-Metros | List of Areas |  |  |  |  | 208000 | DACF | EHU | Waste Mgt | WS |  | imp
2.13.13 | Implement Sanitation Improvement Package (SIP) | All Sub-Metros | SIP Implemented |  |  |  |  | 400000 | DACF | Waste Mgt Dept | ESPA, EHU | WS |  | imp
2.13.14 | Intensify promotion on the arrangements for HH toilets & facilitate the enrolment of 100 HH without toilets | SC4GH Communities | Household (HH) Toilets |  |  |  |  | 20000 | WB | EHU | Beneficiaries/ Assemblymembers | WS |  | imp
2.13.15 | Issue abatement notice to landlords who have not intiated the process of constructing HH toilets & enforce the bye law by prosecuting recalcitrant ones | SC4GH Communities | Abatement notice & prosecution report |  |  |  |  | 20000 | WB | EHU | Legal Team/ SC4GH Team | WS |  | imp
2.13.16 | Procure Solid waste contractors, PPEs, Veronica Buckets, sanitary tools and motorised tricycles | Main Administration | Procurements done |  |  |  |  | 500000 | DACF/ RFG | EHU | Human Resource Unit | WS
2.13.17 | Organize Occupational Health and Safety training and Update the Knowledge of EHOs | Main Administration | Occupational Health and Safety training organised EHOs Knowledge updated |  |  |  |  | 25000 | I.G.F | EHU | Human Resource Unit | WS |  | imp
2.13.18 | Support/Sustain the implementation of street sweeping and drains cleansing | All Sub-Metros | Streets and drains cleaned |  |  |  |  | 2000000 | I.G.F/ DACF | Waste Mgt Dept | Environment |  |  | imp
2.13.19 | Construct 1No. Environmental Court and rehabilitate and furnish 1No. Circuit Court Adum | Bantama Adum | 1No. Environmental Court constructed and 1No. Circuit court rehabilitated |  |  |  |  | 900000 | IGF | Environment | Works | WS |  | imp
2.13.20 | Construct 4no. Institutional WC Toilets at Amankwatia/St. Cyprian/Moshie Zongo/ Bantama | Amankwatia FNT Moshie Zongo Bantama | 4no. WC Toilets constructed |  |  |  |  | 1000000 | DFID | Environment | Works
2.13.21 | Construction of 945 sq meter Reinforced Concrete Ramp for Septage Head Works Ramp | Oti | 945 sq meter Reinforced Concrete Ramp for Septage Head Works Ramp constructed |  |  |  |  | 300000 | DFID | Environment | Works
Development Dimension 3:Environment, Infrastructure and Human Settlement
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 3.1 :Improve efficiency and effectiveness of road transport infrastructure and services
3.1.1 | Pothole patching/ Sectional Repairs along roads in Kumasi | Bantama Subin | Access road |  |  |  |  | 1200000 | GOG | Urban Roads Dept | Works Dept, Beneficiaries | RO | Imp
3.1.2 | Pothole patching & Grading Works along roads in Kumasi | Bompata, S Suntreso, Patase,Manhyia, Nhyiaeso | Access road |  |  |  |  | 3200000 | GOG | Urban Roads Dept | Works Dept, Beneficiaries | RO | Imp
3.1.3 | Resealing of 60km Length of road in the Kumasi Metrolis | Bantama, Subin, Manhyia, Nhyiaeso | Access road |  |  |  |  | 6000000 | GOG | Urban Roads Dept | Works Dept, Beneficiaries | RO | Imp
3.1.4 | Reshaping/ Grading of 60km Roads within the Sub- Metros in the Kumasi Metropolis | All Sub-Metros | Access road |  |  |  |  | 400000 | IGF | Urban Roads Dept | Works Dept/ Beneficiaries | RO | Imp
3.1.5 | Construct 15No. Metal foot bridges over drains/streams in selected communities | All Sub-Metros | 15No. Foot brigdes constructed |  |  |  |  | 750000 | IGF | Urban Roads Dept | Works Dept, Beneficiaries | RO | Imp
3.1.6 | Conduct Surveys and data collection on transport related issues | All Sub-Metros | Quarterly surveys done 8 data collection done |  |  |  |  | 14400 | WB | Transport Dept | Admin |  | Imp
3.1.7 | Institute modalities for the operationalization of mass transit system | All Sub-Metros | Modalities Instituted |  |  |  |  | 2400000 | AFD | Transport Dept | Admin |  | Imp
3.1.8 | Facilitate the construction, upgrade and management of transport infrastructure | All Sub-Metros | Two terminals upgraded, Bollards and Road line markings done |  |  |  |  | 25000 | KMA / GIZ -TUMI Project | Transport Dept | Admin |  | Imp
3.1.9 | Implement the ASToN, MYC and Bloomberg / Healthy Cities Road Safety projects | All Sub-Metros | SUMP plan prepared Reduction in road accidents |  |  |  |  | 3800000 | AFD/Bloomberg | Transport Dept | Admin |  | Imp
3.1.10 | Carryout activities to improve upon public transport services and urban mobility | All Sub-Metros | 12 monthly operations and enforcement activities carried out |  |  |  |  | 12000 | IGF | Transport Dept | Admin |  | Imp
Objective 3.2: Reduce greenhouse gases
3.2.1 | Plant and nurture to growth 5000 trees along water bodies weaving through the Metropolis | All Sub-Metros | 70,000 trees planted |  |  |  |  | 15000 | DACF | EHD | Forestry Dept, EHU, Assembly members | CL | Imp
3.2.2 | Plant and nurture to growth 2500 seedlings in 60 schools | All Sub-Metros | 20,000 trees planted |  |  |  |  | 3000 | IGF | EHD | Forestry, EHU, Assembly members | CL | Imp
3.2.3 | Undertake regular monitoring of planted seedlings and beating up | All Sub-Metros | Monitoring done |  |  |  |  | 1000 | IGF | EHD | Forestry, Assembly members | CL | Imp
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
3.2.4 | Create an Inventory of activities/businesses that generate biomass waste | All Sub-Metros | Inventory created |  |  |  |  | 100000 | DACF/ IGF | Waste Mgt | Planning | CL | Imp
3.2.5 | Create an inventory of Businesses with capacity to convert biomas waste into any form of energy | All Sub-Metros | Inventory |  |  |  |  | 5000 | IGF | Waste Mgt | Planning | CL | Imp
3.2.6 | Quantification of Biomass Waste in the Kumasi Metropolis | All Sub-Metros | Biomas waste quantified |  |  |  |  | 10000 | IGF | Waste Mgt | Planning | CL | Imp
3.2.7 | Facilitate the Construction of Biogas in Institutions & Public Toilets | All Sub-Metros | Biogas provided |  |  |  |  | 150000 | DACF/ IGF | Waste Mgt | Planning | CL | Imp
3.2.8 | Facilitate the Conversion of wood waste from wood processing industries into pellets & briquettes | All Sub-Metros | Wood waste converted into pellets & briquettes |  |  |  |  | 5000 | IGF | Waste Mgt | Planning | CL | Imp
Objective 3.3: Promote proactive planning for disaster prevention and mitigation
3.3.1 | Organize educational campaigns on fire and floods for all filling stations in the Kumasi Metropolis | All Sub-Metros | Public education organized |  |  |  |  | 15367 | DACF | NADMO | NFS,ISD,SW&CD | CL | Imp
3.3.2 | Carryout inspection and evaluation of public/private facilities to ensure safety | All Sub-Metros | Inspections and evaluations carried out |  |  |  |  | 4270 | IGF | NADMO | NFS,ISD,SW&CD | CL | Imp
3.3.3 | Desilt chocked drains and streams | All Sub-Metros | Desilted streams |  |  |  |  | 124150 | DACF | NADMO | Urban Roads/Wks | CL | Imp
3.3.4 | Build the Capacity of NADMO Staff in disaster management | All Sub-Metros | Capacity built |  |  |  |  | 3870 | IGF | NADMO | Waste Mgt, EHU,Stakeholders | CL | Imp
3.3.5 | Organise celebration of World Disaster Day | Selected community | World Disaster Day organized |  |  |  |  | 15974 | DACF | NADMO | Central Administration | CL | Imp
Objective 3.4: Promote a sustainable, spatially integrated, balanced and orderly development of human settlements
3.4.1 | Identify, verify and acquire lease on all lands zoned for public use across the metropolis (phase 1) | All Sub-Metros | Lease |  |  |  |  | 175000 | DACF | PPD | Traditional Authorities, Lands Commission | RO | Not Imp
3.4.2 | Prepare new Planning Schemes for three (3) areas | Buokrom/Duase Daban Ohwim | Planning Schemes |  |  |  |  | 100000 | DACF | PPD | Traditional Authorities, | RO | Imp
3.4.3 | Organize quarterly Statutory Planning Commiittee & Technical Sub Committee meetings | Main Admin | Meetings organized |  |  |  |  | 30000 | DACF | PPD | Committee Members | RO | Imp
3.4.4 | To recruit Fieldworkers and Enumerators for stencilling and data collection | Manhyia North/Bantama | Fieldworkers recruited |  |  |  |  | 160000 | IGF/DACF | PPD | Field Workers |  | Imp
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget | Source | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount |  | Lead | Collaborating
Objective 3.5: Improve quality of life in slums, Zongos and inner cities
3.5.1 | Paving of 1No. Event ground | Dakwadwom | Event grounds paved |  |  |  |  | 200000 | DACF/IGF | Works Dept | Assembly Members |  | Not Imp
Development Dimension 4:Governance, Corruption and Public Accountability
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 4.1: Enhance public safety
4.1.1 | Training On Workplace Corona Virus Disease (COVID-19) Preventive Measures | Main Administration | Metro Guards trained |  |  |  |  | 5000 | DACF/ IGF | Human Resource Unit | Legal Unit | gov | 4340000 | Not Imp
4.1.2 | Maintenance of Security in the Kumasi Metropolis | All Sub-Metros | Security improved |  |  |  |  | 150000 | DACF | Legal Dept | Assembly Members | gov |  | Imp
4.1.3 | Maintenance and provision of Streetlights in the Kumasi Metropolis | All Sub-Metros | Street lights maintained |  |  |  |  | 1000000 | DACF/ IGF | Works Dept. | Assembly Members | gov | 1619500 | Imp
Objective 4.2: Deepen political and administrative decentralization
4.2.1 | Establish Assembly members Electoral Area Assist Funds and Self Help Projects | Main Administration | Fund disbursed |  |  |  |  | 300000 | I.G.F/ DACF | Finance Dept | Administration, Assembly members | gov | 95000 | Imp
4.2.2 | Rehabilitate Assembly's Bungalows/Markets in the metropolis | All Sub-Metros | Buildings |  |  |  |  | 500000 | IGF | Works Dept | Administration |  | 135000 | Imp
4.2.3 | Complete the construction of office accommodation for Nhyiaeso Sub-Metro | Fankyenebra | Office block constructed |  |  |  |  | 400000 | DACF | Works Dept | Administration |  | 1714000 | Imp
4.2.4 | Organize training on GIFMIS | Main Administration | Staff trained |  |  |  |  | 20000 | DACF/ IGF | Human Resource Unit | All Dept |  |  | Imp
4.2.5 | Training Workshop on Local Government Service Protocols | Main Administration | KMA Staff Trained |  |  |  |  | 15000 | IGF/DACF | Human Resource Unit | Assembly members |  |  | Imp
4.2.6 | Facilitate the implementation of One District One Factory in the Kumasi Metropolis | Main Administration | One District One Factory implemented |  |  |  |  | 4500 | IGF/ DACF | Works Dept. | Admin
4.2.7 | Support for administrative activities (Stationary, Fuel, etc) | Main Administration | Support provided |  |  |  |  | 500000 | IGF/ DACF | Central Admin | Finance |  |  | Imp
Objective 4.3: Improve decentralised planning
4.3.1 | Organise training on project management and Monitoring and Evaluation | Main Administration | 40 personnel trained |  |  |  |  | 20000 | DACF/ IGF | Human Resource Unit | Planning, Budget, Procurement, Internal Audit, Finance, Works |  |  | Imp
4.3.2 | Prepare 2021 Annual Action Plan | Main Administration | 2021 AAP prepared |  |  |  |  | 15000 | DACF/ IGF | Planning Unit | All Depts, Assembly members |  |  | Imp
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 4.4:Strengthen fiscal decentralization
4.4.1 | Organise quarterly review meetings with revenue collectors, revenue Officers and revenue Task Force on the performance of IGF | All Sub-Metros | Review meetings organised |  |  |  |  | 8000 | I.G.F | Finance Dept | Revenue Unit, Budget & Rating Dept | gov |  | Imp
4.4.2 | Organize quarterly revenue mobilization campaign on Local FM Stations | All Sub-Metros | Campaign organised |  |  |  |  | 4000 | I.G.F | Finance Dept | Revenue Unit, Budget & Rating Dept, P.R.O | gov |  | Imp
Objective 4.5:Ensure responsive governance and citizen participation in the development dialogue
4.5.1 | Publish Assembly's News Letter & Produce and distribute souvenir of the Assembly | Main Administration | News Letter Published |  |  |  |  | 30000 | IGF | P.R.O | Administration | gov |  | Imp
4.5.2 | Weekly update the Assembly's Website and Organize regular press soirees with the media | Main Administration | website updated |  |  |  |  | 10000 | DACF | P.R.O | ICT | gov |  | Imp
4.5.3 | Organize quarterly Town Hall meetings on Planning and budgeting processes | Main Administration | Meetings organised |  |  |  |  | 20000 | I.G.F | Planning Unit | Budget Dept, P.R.O | gov |  | Imp
4.5.4 | Organise public education /sensitization programme on radio Stations on assembly programmes and activities | All Sub-Metros | Sensitization organised |  |  |  |  | 5000 | I.G.F | P.R.O | All Depts | gov |  | Imp
4.5.5 | Organize quarterly inspection/commisioning ceremony on Assembly projects | All Sub-Metros | Event organised |  |  |  |  | 20000 | IGF | Planning Unit | P.R.O, Works Dept, management, Beneficiaries | gov |  | Imp
Development Dimension 5: Strengthen Ghana's Role in International Affairs
No. | Activities | Location | Output Indicators |  | Time Schedule |  |  | Indicative Budget |  | Implementation Agencies
|  |  |  | 1st | 2nd | 3rd | 4th | Amount | Source | Lead | Collaborating
Objective 5.1:Promote Ghana’s political and economic interests abroad
5.1.1 | Revive all abandoned/dormant International relations | Main Administration | International relations revived |  |  |  |  | 50000 | IGF | International Relations committee | All Heads of Department | gov | Imp
5.1.2 | Support participation of Assembly members & Staff in International Relation activities | National/ International | 15 staff & 10 assembly members supported to participate in International relation activities |  |  |  |  | 300000 | DACF | International Relations committee | All Dept | gov | Imp
Please Note that all Public Private Partnership (PPP) Projects are solely funded by private entities. Estimated funds do not pass through the Assembly's account or system but managed entirely by the private entity. However, the Assembly supervises the construction and ensures the project is built according to agreed designs and specifications.
[8 empty] | review | IMP | NOT
| Total Number of Activities |  | DD1 | 31 |  |  |  | 27 | 27 | 0
|  |  | DD2 | 70 |  |  |  | 58 | 54 | 4
|  |  | DD3 | 37 |  |  |  | 31 | 28 | 3
|  |  | DD4 | 29 |  |  |  | 22 | 20 | 2
|  |  | DD5 | 2 |  |  |  | 2 | 2 | 0
|  |  | Total | 169 |  |  |  | 140